## Sayfa1
PROJECT CHARTER
Name | Developing a personal finance tracker web application
Date | Oct 15, 2023 |  | Project Sponsor | Sakarya University
Last revised | Oct 21, 2023 |  | Project Manager | Ömer Faruk AYDIN
Project Purpose
A web-based personal finance application will allow users to reach from anywhere.
Users will be able to register, login, manage their income and expenses and create budgets.
Allow users to check exchange rates through the application.
Project Definition
Financial Management Solution: The "Personal Finance Tracker" is a web-based financial management solution designed to help users manage their income and expenses. It offers tools for tracking, budgeting, visualizing financial data and viewing global exchange rates.
User-Friendly Budgeting Platform: This platform prioritizes user experience by offering an interface for setting, tracking, and adjusting personal budgets. Users can input income and expenses, and the system provides easy-to-understand data visualizations to facilitate informed financial decisions.
Collaborative Development and Communication: The project is a result of collaborative efforts, with regular communication among team members and stakeholders. The addition of the global exchange rate feature enriches the user experience and satisfy their expectations.
Security and Regulatory Compliance: Users can rely on the exchange rate feature while ensuring their financial information's confidentiality.
Team Members & Roles
Ömer Faruk AYDIN B201202023 |  | Project Manager, Back-end Developer, Tester, Organizer
Burak ALATAŞ B201202018 |  | Back-end Developer, Tester, Technical Support
Muhammet Ali ÇABUK B201202060 |  | Back-end Developer, Documentation Support
Yiğit SERT B201202041 |  | Front-end Developer, Documentation Organizer
Yunus Emre GÜLTEPE B201202022 |  | Front-end Developer, Budget Organizer
Nisanur BAŞTOR B201202044 |  | Front-end Developer, Documentation Organizer
Project Budget
TASK | STATUS | BUDGET | ACTUAL | UNDER/OVER
Planning | In Progress | $1,000 | $500 | $500
Development | On Hold | $5,000 | $- | $(5,000)
Testing |  | $500 | $- | $(500)
Deployment |  | $2,500 | $- | $(2,500)
Maintainance |  | $5,000 | $- | $(5,000)
Project Management |  | $2,500 | $- | $(2,500)
Wages |  | $10,000 | $250 | $(9,750)
TOTAL |  | $26,500 | $750 | $(25,750)
Major Milestones & Target Dates of Milestones |  |  | Success Criteria
Project Initiation | (Week -1)16.10.2023-22.10.2023 |  | Delivery in 9 weeks.
User Registration and Login | (Week 2-3)23.10.2023-5.11.2023 |  | %100 implementation of all defined functional requirements.
Income and Expense Tracking | (Week 4 -5)6.11.2023-19.11.2023 |  | User satisfaction rating of at least 4 out of 5 based on feedbacks.
Exchange Rate Implementation | (Week 6)27.11.2023-3.12.2023 |  | At least %90 accuracy rate in exchange rates feature
Designing | (Week 7)4.12.2023-10.12.2023
Data Visualization & Finalizing Project | (Week 8-9)11.12.2023 - 24.12.2023
Risks |  |  | Constraints
Inaccurate time estimates |  |  | Needs to be done in atmost 10 weeks
Task-employee conflicts |  |  | Creating a full documentation of the project is a must
Lack of proper planning
Changing requirements |  |  | Every project member has to know about other members' responsibilities
Lack of technological adaptation
The availability of exchange rates server may be limited which can effect performance
Dependencies
1)Task Dependencies: Dependency on the completion of user authentication and authorization tasks, expense and income management, availability of income and expense data. Completion of external API integration for currency exchange rates. |  |  | 3)Data Dependencies: User registration and login processes depend on user data, income and expense features rely on financial transaction data, exchange rate tracking relies on up-to-data from external sources(e.g. currency exchange rate APIs.)
2)Resource Dependencies: A database server which all data will be stored, a web server where application will be hosted,a java development environment to develop the app, staff who are developers, designers and tester for the project to proceed |  |  | 4)Temporal Dependencies: There may be deadlines associated with project milestones such as completion of user registration, data visualization and such. Certain tasks may have scheduling constraints, like ensuring that user data is available before implementing user registration and login features.
Technologies Will Be Used For Software Development & Project Management
Programming Languages | Java, Javascript |  | Java | Spring Boot, JPA, Hibernate, Lombok
Web Technologies | Bootstrap, HTML5, CSS, Javascript |  | UML Tools | Star UML
Web Services | REST API, Axis |  | IDE | IntelliJ Idea, Visual Studio Code
Database | MySQL |  | Project Planning & Management | Jira, Confluence
Version Control | Git |  | Build Tools | Maven
Application & Web Servers | Apache Tomcat |  | Issue Management Tools | Jira
Communication Channels of Team Members & Stakeholders |  | Daily meetings via Discord. Jira and Confluence for issues, errors and bugs. Whatsapp for urgent actions mostly.